Main functions include:

•	Shutting down a building under tight deadlines.

•	Anticipating the need for additional resources and requesting them in a timely manner.

•	Working closely with the Resident Engagement Team Leader.

•	Assisting with evacuations as needed.

•	Conducting damage assessments.

The Building Protection Team Leader takes all actions necessary to protect the infrastructure of an assigned building, including electrical, mechanical, water, steam, gas and elevator systems.

READY TO RESPOND DISASTER STAFFING TOOLKIT

# Building Protection Team Leader

# Job Action Sheet

| 96 Hours Pre-Event Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Receive Section Meeting announcement from Housing Chief. |  |  |  |
| Read entire Job Action Packet with tools and fill gaps as needed. |  |  |  |
| Update all tools including Building Shutdown and Re-open Checklist, Building Equipment Inventory Worksheet, Building Emergency Kit Worksheet, Critical Vendor Contact List and Building Readiness Report. |  |  |  |
| Send Building Readiness Report to Housing Chief. |  |  |  |
| Confirm current contact information of staff with Housing Chief. |  |  |  |

Enterprise Community Partners, Inc.

Name _______________________________  Phone _____________________ Date last revised _____________________

72 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Attend Housing Section Meeting. |  |  |  |
| Update Building Readiness Report and Building Equipment Inventory Worksheet (including photographs) and send to Housing Chief. |  |  |  |
| Review Building Shutdown and Re-open Checklist and Building Emergency Kit Worksheet. |  |  |  |
| Review and update Critical Vendor Contact List. Contact vendors as necessary regarding availability of services. (Insurance adjusters will need to inspect damage before repairs can begin.) |  |  |  |
| Obtain Payment Card from Housing Chief to purchase necessary supplies within cost limits. For supply needs beyond cost limits, coordinate with Housing Chief. |  |  |  |
| Coordinate with Resident Engagement Team Leader on flyers to alert and update residents about planning and services. Help distribute flyers. |  |  |  |
| Assess need for additional staff or volunteers and communicate to Housing Chief. |  |  |  |

Enterprise Community Partners, Inc.

72 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| If evacuating, prepare timeline for building shutdown and share with Resident Engagement Team Leader. If not, coordinate with Resident Engagement Team Leader on plans and stay-teams. Communicate plans to Housing Chief. |  |  |  |

Enterprise Community Partners, Inc.

48 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Attend Housing Section Meeting. |  |  |  |
| Assess need for additional staff or volunteers and communicate to Housing Chief. Set up building check-in location for volunteers. |  |  |  |
| Verify that staff understand roles in helping protect equipment in Building Equipment Inventory Worksheet and tasks to be performed on Building Shutdown and Re-open Checklist. |  |  |  |
| Begin periodic building walk-throughs, checking for evacuated units. Once verified, mark evacuated units with duct tape across door frame, door and handle when. Coordinate with Resident Engagement Team Leader. |  |  |  |

Enterprise Community Partners, Inc.

24 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Attend Housing Section Meeting. |  |  |  |
| Update Building Shutdown and Re-open Checklist and Building Readiness Report. |  |  |  |
| If not evacuating, confirm stay-team assignments. |  |  |  |
| Request number and location of residents sheltering in place from Resident Engagement Team Leader. Assist with apartment checks as needed. |  |  |  |
| Confirm building shutdown time with Resident Engagement Team Leader and report to Housing Chief. Provide plan to fill in gaps. |  |  |  |

Enterprise Community Partners, Inc.

12 Hours

Pre-Event

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Update Building Shutdown and Re-open Checklist and report to Housing Chief. |  |  |  |
| Check in with Resident Engagement Team Leader to get final count of residents and staff remaining in building through disaster; report to Housing Chief. |  |  |  |
| If applicable, conduct rounds to check on any remaining residents with Resident Engagement Team Leader. Alert residents to take necessary precautions. |  |  |  |

Enterprise Community Partners, Inc.

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Conduct building walk-throughs when safe and appropriate. Assess and document damage and make repairs in accordance with insurance protocols. |  |  |  |
| Assess need for additional staff or volunteers and communicate need to Housing Chief. |  |  |  |
| Get update from Resident Engagement Team Leader on status of remaining residents. |  |  |  |
| Attend Housing Section Meeting, via conference call if necessary. |  |  |  |
| Work with Resident Engagement Team Leader to plan for residents to return or extend their evacuation. |  |  |  |

EVENT

Stay on Alert

# Immediately

# Following Event

EVENT/

Immediately Following Event

Enterprise Community Partners, Inc.

12 Hours

Post-Event

Enterprise Community Partners, Inc.

| Action | Date | Notes | Done |
| --- | --- | --- | --- |
| Attend Housing Section Meeting. |  |  |  |
| Receive update from Housing Chief on visits from contractors or insurance inspectors. |  |  |  |
| Continue repairs as and call in necessary vendors and support resources. Work closely with Housing Chief to determine documentation needs. |  |  |  |
| Consult with external professionals including engineering and trade specialists. Once external professionals have approved, begin reopening building. If building has sustained extensive damage, this may take weeks or months. |  |  |  |
| Update Resident Engagement Team Leader on assessment of damages and infrastructure and receive update on remaining residents. |  |  |  |
| If needed, open check-in area to take in volunteers and supplies. |  |  |  |